## Plan (AWS)
Category | Tasks / Milestones | Status | Owner | Level of Effort | Date | Progress Notes | Reference Details | Terraform (where applicable)
UC Setup | Configure S3 bucket and IAM role for UC to store and access managed table |  |  | Low |  |  | Getting started | Deploying pre-requisite resources and enabling Unity Catalog
UC Setup | Create Metastore in Databricks account per region |  |  | Low |  |  | Create Metastore | Create a Unity Catalog metastore and link it to workspaces
UC Setup | Assign workspaces to Metastore |  |  | Low |  |  | Enable Workspace to Metastore
User Management | Identify and assign main roles: - Account Admin - Metastore Admins - Workspace Admins |  |  | Low |  |  | Admin details | Account admin: grant "account_admin" role to group or user Metastore admin: set group or user as metastore owner Workspace admin: set databricks_permission_assignment "ADMIN" to groups or users
CHECKPOINT
User Management | Set up SCIM provisioning with Okta, AAD etc. at Account level |  |  | Medium |  |  | Sync users and groups from your identity provider ¦ Databricks on AWS
User Management | Access Refactor - Migrate workspace groups to account level. - Use Terraform/SCIM api/3rd party SCIM app to create account level groups with same name as the workspace level groups that need to be migrated - Use Databricks UCX to inventory and back up workspace level groups' entitlements and permissions - Use Databricks UCX to assign new account groups to workspace and apply same entitlements and permissions from the backup - Use Databricks UCX to clean up backup and inventory |  |  | High |  |  | While all users are elevated to account level with Identity Federation, workspace level groups are kept as is. So workspace level groups to account level group migration is required in following cases: - You want to use the same group for both account level access control (workspace access, UC objects etc.) and workspace level access control (clusters, notebooks, dashboards etc.) - You are using SCIM integration with identity provider (AD, Okta etc.) to manage groups. Becasue SCIM integration will be configured in account level, you need to migrate workspace groups to account groups so they will be manaded by the SCIM integration. - No new workspace level groups can be created going forward, it's better to consolidate all groups to account level groups. If you will use Terraform to manage account group to workspace assignment, workspace level permission control, you will need to import the changes made by UCX to sync the Terraform state. See import groups to workspace assignment and workspace level permissions. | Groups to workspace assignment Workspace level permission control Managing groups/users/service principals using, see Security section in the document
User Management | Enable SSO at account console (OIDC/SAML) and SSO unified login (public preview) to workspaces |  |  | Low |  |  | Set up SSO for your workspace ¦ Databricks on AWS
CHECKPOINT
Integrate with governance partners | Plan out Integration with partners Immuta, Privacera, purview etc.
CHECKPOINT
UC Design | Create assessment dashboard for workspace: - Install Databricks UCX, following the readme and this interactive tutorial - The installation will deploy assessment jobs crawling infomation about the workspace and generate assessment dashboard for clusters, jobs, databases/tables, dbfs mounts, cloud storages, workspace permissions. Please check this interactive tutorial |  |  | Medium |  |  | Databricks UCX UCX installation interactive tutorial UCX assessment report interactive tutorial
UC Design | Create inventory of all tables in hive metastore (internal/external) |  |  | Low |  |  | use this script - https://github.com/databrickslabs/ucx/tree/0bf43e73b48a7100dfd3010ce76802c94cc66c4b
UC Design | Identify obsolete tables (empty, test tables, poc tables etc ) |  |  | Low |  |  | Add column "Obsolete" to above inventory and mark the obsolete table as Y for recording purpose
UC Design | Choose a database/business function as pilot /phase 1 |  |  | Medium
UC Design | Segregate tables into - Delta (External/managed), Parquet, Others |  |  | Low |  |  | The inventory script will help you with that...but create pivot tables on top of the list to understand the different formats currently being used in your env. This will help you understand what migration patterns will you be leveraging.
UC Design | Catalog workspace isolation strategy |  |  | Low |  |  | Catalog¦workspace binding
UC Design | UC catalog structure: - list of catalogs - naming conventions for catalog - S3 path for any defaults for managed table - Define Schema/databases |  |  | Low |  |  | UC Design Best Practices
UC Design | Identify requirements and strategy for external locations and storage credentials. |  |  | Low |  |  | How to identify the need for external location. - How important is ability to govern the access to subdirectories where external tables can be created, files can be read and written to. - It can be as granular as one external location for every subdirectories - As broad s one external location per bucket - Middle ground - External locations setup that gives you the best data isolation for the users that have permissions to write/read from
UC Design | Identify requirements for setting up Volumes to be able to manage S3 locations in Catalog via UC | [5 empty] | Volumes
UC Design | Decide on target tables - will it be all external or managed to be consistent across. |  |  | Low
CHECKPOINT
UC Enablement - Upgrading Metastore | Create storage credentials and external locations |  |  | Low |  |  | Manage external locations and storage credentials ¦ Databricks on AWS | Storage credentials External locations
UC Enablement - Upgrading Metastore | Catalog Creation (define the S3 path for catalog or let it be default) |  |  | Low |  |  | Create and manage catalogs ¦ Databricks on AWS | Catalog
UC Enablement - Upgrading Metastore | Schema Creation (define the S3 path for schema or let it be default) |  |  | Low |  |  | Create and manage schemas (databases) ¦ Databricks on AWS | Schema
UC Enablement - Upgrading Metastore | Create UC enabled clusters and validate UC is enabled |  |  | Low |  |  | Cluster access mode | Create cluster with data_security_mode set
UC Enablement - Upgrading Metastore | Table migration from Hive Metastore to UC for all table types. | [5 empty] | Patterns
| External table:use sync command for external tables |  |  | Medium |  |  | SYNC command
| Managed table but stored in s3 bucket/dbfs mount - use sync with setting spark.databricks.sync.command.enableManagedTable=True |  |  | Medium
| Managed table stored in DBFS root - use delta deep clone or CTAS OR rewrite as Delta external and then SYNC |  |  | High
UC Enablement - Upgrading Metastore | Create and Setup managed and External Volumes |  |  | Low |  |  | Volumes | Volume
UC Enablement - Upgrading Metastore | Views: manually create views. |  |  | Medium |  |  | Upgrade tables and views to Unity Catalog ¦ Databricks on AWS | databricks_sql_table for table or view
UC Enablement - Upgrading Metastore | Move all external to managed UC tables - to standardize across (optional) |  |  | Medium
UC Enablement - Permissions and ACLs | Set up permissions at table, volumes, functions, database and catalog level |  |  | Medium |  |  | Permissions in UC | Grant permission
CHECKPOINT
UC Enablement - Upgrading Analytical workload | Gold Layer Consumers: Upgrade downstream queries (3rd Party BI tools/dbsql) to use the new catalog/database/table structure |  |  | Medium
UC Enablement - Upgrading workloads | Setup Cluster policies to enforce cluster to have UC eligible access mode (optional) |  |  | Medium |  |  | Unity Catalog best practices ¦ Databricks on AWS (Can execute migration on one Database before moving to the others) | Cluster policy
UC Enablement - Upgrading workloads | Silver Layer Consumers/Gold layer Producers: Upgrade Jobs with the right UC clusters and point to new UC tables- - Use Single User mode for jobs cluster - Set Service principal (SP) as owner of the prod jobs and run as that SP |  |  | High
UC Enablement - Upgrading workloads | Bronze Layer Consumers/Silver Layer Producers: Upgrade Jobs with the right UC clusters and point to new UC tables- - Use Single User mode for jobs cluster - Set Service principal (SP) as owner of the prod jobs and run as that SP |  |  | High
UC validation | Validate the entire setup - tables and data is fine - Jobs run fine - Creation of Compute run fine - Any 3rd party tool accessing data/tables works fine - User permissions and access |  |  | High
CHECKPOINT
UC Enablement | Repeat all the steps/script from Phase 1 to the remaining data assets |  |  | High
Validation | Validate the entire setup - tables and data is fine - Jobs run fine - Creation of Compute run fine - Any 3rd party tool accessing data/tables works fine - User permissions and access |  |  | High
Go-Live | Go-Live

## Migration patterns
Format | Type | Location | migration mechanism | rewrite data required?
delta | external | s3 | use SYNC to generate external tables in UC
delta | managed | s3 | use SYNC to generate external tables in UC (DBR 13+, set spark.databricks.sync.command.enableManagedTable=true;)
delta | managed | dbfs root | rewrite to external delta table in UC using deep clone or CTAS. | Yes
delta | managed | dbfs (s3 mounts) | change to s3 location in glue, rewrite to external UC table
parquet | external | s3 | use SYNC to generate external tables in UC. Optional: run periodic SYNC to make sure schema changes made in Glue are reflected in UC
parquet | managed | s3 | generate create table statements using SHOW CREATE TABLE and recreate in UC as external table
parquet | - | dbfs | rewrite to external UC table, preferably delta (evaluate writers and readers) | Yes
hive (MapredParquetOutputFormat) | external | s3 | recreate in UC as external parquet table.
hive (HiveIgnoreKeyTextOutputFormat) | external | s3 | rewrite to external UC table, preferably delta (evaluate writers and readers) | Yes
hive (HiveSequenceFileOutputFormat) | external | s3 | rewrite to external UC table, preferably delta (evaluate writers and readers) | Yes
hive | managed | s3 | convert to external
views | views | - | recreate in UC using 3 layer namespace table references.